## Instructions
PROTECTED A (when completed)
Instructions for Developing a Build-up Budget
The audit team is responsible for establishing a budget based on the audit work required, and for monitoring the actual amounts against the budget.
1. To create a built-up budget, determine the total hours needed to complete the audit work using the "Built-up Budget" tab in this Excel document. This template was prepared to help the audit team estimate the level of effort needed to complete its audit work (by audit team member, fiscal year, audit phase, line of enquiry). This template can be adapted to the team's needs. Use the tasks in your detailed audit programs to estimate the hours needed for the examination phase.
Before adapting the template, please ensure that pre-programmed formulas remain accurate when adding or deleting lines and/or columns.
Budgeting should be done by fiscal year. The template is set up to facilitate this.
Staff who are full time on the audit can be budgeted at 85% to allow time for other office responsibilities.
By week:
5 days x 7.5 hrs = 37.5 hrs @ 85% = 32 hrs
By month:
21 days x 7.5 hrs = 157.5 hrs @ 85% = 134 hrs
2. Complete the "Overall Audit Budget" tab based on the established budget for the Audit Report Submission and the revised estimated budget using the built-up budget.

## Built-up Budget
PROTECTED A (when completed)
[Insert Audit Report's Title]
|  |  | Fiscal Year (FY) 1: 20..-20.. | [12 empty] | Fiscal Year (FY) 2: 20..-20.. | [12 empty] | Fiscal Year (FY) 3: 20..-20..
Line of Enquiry | Level | Name | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March | TOTAL FY1 | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March | TOTAL FY2 | April | May | June | July | August | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March | TOTAL FY3 | TOTAL FOR THE AUDIT
Planning Phase |  | (See Instructions) | [12 empty] | TOTAL FY1 | [12 empty] | TOTAL FY2 | [12 empty] | TOTAL FY3 | TOTAL FOR THE AUDIT
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
Total Planning Phase hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Examination Phase |  | (See Instructions) | [12 empty] | TOTAL FY1 | [12 empty] | TOTAL FY2 | [12 empty] | TOTAL FY3 | TOTAL FOR THE AUDIT
LOE #1 - [Insert Title]
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Total LOE #1 - Exam Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LOE #2 - [Insert Title]
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Total LOE #2 - Exam Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LOE #3 - [Insert Title]
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
|  | Total LOE #3 - Exam Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Examination Phase hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reporting Phase |  | (See Instructions) | [12 empty] | TOTAL FY1 | [12 empty] | TOTAL FY2 | [12 empty] | TOTAL FY3 | TOTAL FOR THE AUDIT
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
| [Insert Level] | [Insert Team Member's Name] | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 0
Total Reporting Phase hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTAL FOR THE AUDIT (hours) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Overall Audit Budget
PROTECTED A (when completed)
AUDIT REPORT BUDGET
TOTAL ESTIMATED BUDGET (From Audit Report Submission) | Hours | Contract | Travel
Planning Phase(1)
Examination/Reporting Phase
Total Estimated Budget (A) | 0 | 0 | 0
| FY 1: 20.. - 20.. |  |  | FY 2: 20.. - 20.. |  |  | FY 3: 20.. - 20.. |  |  | GRAND TOTAL FOR THE AUDIT (B)
TOTAL REVISED BUDGET | Hours | Contract | Travel | Hours | Contract | Travel | Hours | Contract | Travel | Hours | Contract | Travel
Planning Phase - Actual(1) | [9 empty] | 0 | 0 | 0
Examination Phase – Estimated | [9 empty] | 0 | 0 | 0
Reporting Phase – Estimated | [9 empty] | 0 | 0 | 0
Total Revised Budget (B) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Increase or decrease to Total Estimated Budget (B)-(A) | [9 empty] | 0 | 0 | 0
(1) Explain any variances greater than 15% between planned and actual for Planning Phase

## SecurityLabel (hidden)
UNCLASSIFIED
NON CLASSIFIÉ
PROTECTED A
PROTÉGÉ A
PROTECTED B
PROTÉGÉ B
PROTECTED A (when completed)
PROTÉGÉ A (lorsque complété)
PROTECTED B (when completed)
PROTÉGÉ B (lorsque complété)